## Product Launch Checklist
| Activity | Status (Green/Yellow/Red) | Owner/Name | Audience | Details, Deliverables, & Artifacts | Due Date | Reference Due Date from Release Date | Tier 1 | Tier 2 | Tier 3
Plan | Identify the Cross-Functional Launch Team | Pending | Executive Team | Internal |  |  | -150 Days | X
| Schedule Launch Kickoff - 90mins | Pending | Executive Team | Internal |  |  | -150 Days | X
| Kickoff Meeting - Create/Review Customer Problem Statement | Pending | Launch Team | Internal |  |  | -130 Days | X | X | X
| Kickoff Meeting - Create/Review Business Success Alignment (KPIs) (ex. Product Unit Economics) | Pending | Launch Team | Internal |  |  | -130 Days | X | X | X
| Kickoff Meeting - Create Responsibilities & Working Agreements of Launch Team (Operationalize) | Pending | Launch Team | Internal |  |  | -130 Days | X
| Kickoff Meeting - Establish the Budget, Launch Timeline, Territories, Activities, Dependencies, and Risks | Pending | Launch Team | Internal |  |  | -130 Days | X | X | X
| Brief Executive Team on Plan | Pending | Launch Team | Internal |  |  | -120 Days | X | X
| Company All Hands: Communicate and align to company on the goal and launch timeline | Pending | Executive Team | Internal |  |  | -120 Days | X | X
Execute | Product Readiness
| Product Development Delivery Plans (ex. encompasses idea to delivery including all R&D functions) | Pending | Product Management/Engineering & Operations/UX | Internal |  |  | Iterative | X | X | X
| Product Name Determination | Pending | Product Marketing | Internal |  |  | -75 Days | X
| Competitve Analysis and User Research | Pending | Product Management/Product Marketing/UX | Internal |  |  | -60 Days | X
| Product Pricing and Packaging Established and Tools Updated | Pending | Product Management/Product Marketing | Internal |  |  | -30 Days | X | X
| Beta Program (Identify, secure, collect feedback from customers, etc.) | Pending | Product Management | External |  |  | -7 Days | X | X
| Go/No Go Decision on Release | Pending | Launch Team | Internal |  |  | -7 Days | X
| Internal Communication - To All Employees about the Product Launch Coming | Pending | Product Marketing/Product Management | Internal |  |  | -5 Days | X | X
| Internal Communications - To Channel & OEM about the Product Launch Coming | Pending | Product Marketing/Product Management | Internal |  |  | -5 Days | X | X
| External Communications - Analyst Briefs (may need to do by Region ex. EMEA vs APAC) | Pending | Product Marketing/Product Management | External |  |  | -3 Days | X | X
| Create and Implement Product Feedback Loops (NPS, Usage, etc.) | Pending | Product Management/Engineering/Customer Success | Internal |  |  | Launch Date/GA | X | X
| Internal Documentation (ex. Technical Documentation, Wikis, etc.) | Pending | Product Management/Product Marketing/Engineering | Internal |  |  | Launch Date/GA | X | X | X
| External Documentation (User Documentation, Release Notes, Upgrade Process, Roadmaps, etc.) | Pending | Product Management/Product Marketing/Engineering | External |  |  | Launch Date/GA | X | X | X
CS, Partner & Sales Readiness
| Current Database Analysis to Create Target Accounts (Prospects, Active Pipeline, Current Customers) | Pending | Sales Ops, CS. Sales | Internal |  |  | -100 Days | X | X
| Sales Training and Tools Plan | Pending | Sales Ops | Internal |  |  | -60 Days | X | X
| Support Training and Tools Plan | Pending | CS | Internal |  |  | -60 Days | X | X
| Development of Sales Training Materials | Pending | Sales Ops/Product Marketing | Internal |  |  | -21 Days | X | X | X
| Development of Technical Field Training Materials | Pending | Services/CS/Product Marketing | Internal |  |  | -21 Days | X | X | X
| Partner Enablement (Internal, Channel, SIs, Reseller) | Pending | Partner/Product Marketing | External |  |  | -21 Days
| Sales Enablement (Internal, Inside Sales and/or Field) | Pending | Sales Ops/Product Marketing | Internal |  |  | -14 Days | X | X | X
| Technical Field Enablement (Internal and Channels & Partners) | Pending | Services/CS | External |  |  | -14 Days | X | X | X
| Community Communications (Email, Posts & Content) | Pending | CS/Product Marketing | External |  |  | -14 Days
| Update SDR Outreach/Cadences (Sales Engagement Software, Chatbots, Email, etc.) | Pending | Sales Ops/Sales/Marketing | Internal |  |  | -7 Days
| Product Demo Scripts/Videos and Environments Created/Updated | Pending | Product Management/Product Marketing | Internal |  |  | Launch Date/GA | X | X
| Customer Facing Documentation/Help Articles | Pending | CS/Product Management/Engineering | External |  |  | Launch Date/GA | X | X
| CS Escalation Path Defined, Communicated, and Implemented | Pending | CS/Product Management/Engineering | Internal |  |  | Launch Date/GA | X | X
Marketing Readiness
| Brand Campaign to Create Market Awareness | Pending | Brand & Comms/Product Marketing | External |  |  | -120 Days | X
| Integrated Campaigns Targeting Top Segments and Accounts | Pending | Demand Gen/Product Marketing | External |  |  | -120 Days | X | X
| SEO to Identify Top Keywords for Content | Pending | Demand Gen/Product Marketing | Internal |  |  | -120 Days | X | X
| Thought Leadership Strategy, Calendar, Deliverables | Pending | Product Marketing/Marketing | External |  |  | -120 Days | X | X | X
| Events Roadmap (including 3rd Party and Hosted) including Virtual, Webinars and In-person | Pending | Demand Gen | Internal |  |  | -120 Days | X | X
| Collateral (Overview of Product Presentation, DataSheets, Competitve Positioning, Playbooks, etc.) | Pending | Product Marketing | Internal |  |  | -90 Days | X | X | X
| Digital Asset Creation (Videos, Graphics, Emails, Ads, etc.) | Pending | Brand & Comms/Demand Gen | Internal |  |  | -90 Days | X | X | X
| Launch Teaser Drop #1 (60 Days Before) | Pending | Brand & Comms | External |  |  | -60 Days | X
| Company Website Update (Including International Variants) | Pending | Product Marketing | External |  |  | -45 Days | X | X
| Thought Leadership & Content Website (Including International Variants) | Pending | Product Marketing | External |  |  | -45 Days | X
| Launch Teaser Drop #2 (30 Days Before) | Pending | Marketing Org | External |  |  | -30 Days | X | X
| Finalize Customer Onboarding Flow and Nurture (Emails, Chatbot, In-Product Notifications | Pending | Product/Product Marketing/Marketing Ops | External |  |  | -30 Days | X
| Update Existing Nurture Streams and Automation (Emails, Chatbot, In-Product Notifications, etc.) | Pending | Marketing Ops/Demand Gen/Product Marketing | External |  |  | -30 Days | X | X | X
| Sales/Partner/Support Kit (Selling Deck, Battle Cards, Press Release, Customer Notification Comms, Onboarding Collateral (Demos, etc.) | Pending | Product Marketing | Internal |  |  | -30 Days | X | X
| External Communications such as Blogs, Owned Social Media, etc. | Pending | Brand & Comms/Demand Gen | External |  |  | -30 Days | X | X | X
| Press Release & Outreach | Pending | Brand & Comms/Product Marketing | External |  |  | -30 Days | X | X
| Analyst Briefings (Gartner, Forrester, 451, etc.) | Pending | Analyst Relations/Product Marketing | External |  |  | -30 Days | X | X
| Paid Digital Campaigns (Paid Search, Paid Social, Content Syndication, etc.) | Pending | Demand Gen | External |  |  | Launch Date/GA | X | X
| Flagship Launch Event (Keynote, Lightning Strike, etc.) | Pending | Marketing Org | External |  |  | Launch Date/GA | X | X
Ops/G&A Readiness
| Finance - Tax | Pending | Finance | Internal |  |  | -30 Days | X
| Finance - Billing & Invoicing | Pending | Finance/Product Management | Internal |  |  | -30 Days | X | X | X
| Legal - Contract Creation and Updates, SLAs, etc. | Pending | Legal/Product Management | Internal |  |  | -30 Days | X
| Back Office IT Systems (CRM updates, etc.) | Pending | IT | Internal |  |  | GA | X | X | X
Monitor | Revisit strategic goals of product and launch success (Solidify/Modify Unit Economics for the Product) | Pending | Product Marketing/Product Management/Executive Team | Internal |  |  | Post Launch Date/GA | X | X | X
| Revisit what we are measuring across the business per department (ex. Hiring Plans, SLAs, CSAT, etc.) | Pending | Product Management | Internal |  |  | Post Launch Date/GA | X | X
| Post Launch Communications & Campaigns | Pending | Marketing | External |  |  | Post Launch Date/GA | X | X
| Ensure capacity is available for Engineering and Operations to ensure smooth launch | Pending | Engineering | Internal |  |  | Post Launch Date/GA | X | X
| Ensure capacity is available for the Tail of the launch (ex. bugs, configs, enhancements, etc.) | Pending | Product Mangement/Engineering | Internal |  |  | Post Launch Date/GA | X | X | X
| Party! | Pending | Company | Internal |  |  | Post Launch Date/GA | X | X
| Integrate the New Product into Existing Operations | Pending | Company | Internal |  |  | +1 Quarter | X

## Key Terms & Definitions
Product Launch Stages | Commentary
Plan | Get Organized. Create the cross-functional team, establish how we will operate, and what success looks like. Establish the Product Launch Plan.
Execute | Communicate the Plan across the Org. Execute the Product Launch Plan across functions. Be Agile.
Monitor | Execute on Post Launch Activities including monitoring adoption, product feedback, key success metrics, etc. to get to business as usual.
Audience
Internal | All internal stakeholders including executive leadership, relavent departments, relevant agencies, the board and investors.
External | All external stakeholders including customers, community, partners, prospects, suppliers, industry analysts, the press and competitors.
Categories
Product Readiness | Within this category activites are performed by Product, Engineering, and Product Marketing.
Service & Sales Readiness | Within this category activites are performed by Services Team, Sales, Support, and Product Marketing.
Marketing Readiness | Within this category activites are performed by Product, Product Marketing, and Corporate Marketing.
Ops & G&A Readiness | Within this category activites are performed by Finance, Legal, and Internal IT Systems.
The Launch Team
Product Marketing (Launch Quarterback) | The point person/decision maker for the launch. Determines launch tier, manages timeline, and readiness across all teams, and is responsible for communicating benefits to all internal and external stakeholders.
Product | Responsible for delivering the product against the strategic objectives of the launch.
Engineering | Responible for the "how this is built" including owning the architecture, feature set, and delivery timeline.
Marketing | Responsible for amplifying the messaging through demand gen campaigns and executing upon PR and AR.
Sales | Responsible for positioning the new product/features to new prospects and communicating to existing pipeline and cross-sell/upsell.
Customer Support/Success | Responsible for communicating to existing customers, supporting new users through onboarding and ensuring that customers achieve success.
Support | Prepared to address any break-fix issues that could arise from the new product/features.
Partner | Responsible for educating both upstream and downstream technology integration partners as well as enabling channel/SIs/resellers, where applicable.
Launch Types
Tier 1 | Full public launch to bring a brand new product to market.
Tier 2 | Within a current product, delivery of a new capability or a feature/ feature sets that are GA.
Tier 3 | Within a current product, delivery of a minor feature/update with limited customer impact.
Task Status
Pending | Task may be on the roadmap, but lacks a scope, plan and timeline.
Scheduled | Task has a plan and team consensus has been reached on scope and timeline.
On Track | Task has been started and is currently on track to meet goals.
Monitor | Task may be falling behind schedule or short of original scope. Additional clarity should be provided on a regular cadence until back on track.
Stuck | Task is currently stuck and is at risk. The owner needs to prioritize fixing or the task should be reevaluated.
Completed | Task is complete!